## Overview
GBS / SSC TRANSFORMATION — DELIVERABLE INVENTORY
PURPOSE
Master inventory of consulting-standard deliverables for a GBS/SSC transformation program.
Organized by 5 phases: Assess → Design → Build → Transition → Optimize.
Within each phase: deliverables grouped by workstream (Process, People, Technology, Governance, Change, Location, Finance).
Use as: project planning checklist, scope definition tool, quality gate tracker, consultant briefing reference.
THE FIVE PHASES
Phase 1 — ASSESS: Current state discovery, data collection, feasibility, stakeholder mapping. Duration: 8–12 weeks.
Phase 2 — DESIGN: Target Operating Model, business case, location strategy, governance blueprint. Duration: 10–16 weeks.
Phase 3 — BUILD: Site setup, recruitment, IT infrastructure, process documentation, training development. Duration: 16–24 weeks.
Phase 4 — TRANSITION: Knowledge transfer, parallel run, go-live, hypercare. Duration: 12–20 weeks per wave.
Phase 5 — OPTIMIZE: Stabilization, CI program, automation pipeline, scope expansion, maturity assessment. Duration: Ongoing.
THE SEVEN WORKSTREAMS
PROCESS: Process taxonomy, scope definition, standardization, documentation, SLAs/KPIs.
PEOPLE & ORG: Talent mapping, org design, job architecture, recruitment, retention, reskilling.
TECHNOLOGY: System inventory, IT requirements, tool selection, integration, access management.
GOVERNANCE: Decision rights, escalation, reporting, steering committee, risk management.
CHANGE & COMMS: Stakeholder analysis, communication plan, change readiness, training, Betriebsrat.
LOCATION & INFRA: Location assessment, site selection, office setup, facilities, BCP/DRP.
FINANCE & BUSINESS CASE: Cost modeling, benefits tracking, business case, value realization.
HOW TO USE
1. Review the full inventory on the 'Deliverable Inventory' tab.
2. Mark deliverables as 'In Scope', 'Out of Scope', or 'Deferred' for your program.
3. Assign owners and target dates for in-scope deliverables.
4. Use the Status column to track progress: Not Started → In Progress → In Review → Complete.
5. Filter by Phase or Workstream to create workstream-specific checklists.
6. The 'Enablers' tab lists cross-cutting prerequisites that must be resolved before transition.

## Deliverable Inventory
GBS / SSC TRANSFORMATION — COMPLETE DELIVERABLE INVENTORY
YELLOW columns (I–L) are your project tracking fields. Filter by Phase or Workstream to create focused checklists.
Phase | Workstream | # | Deliverable | Description | Typical Owner | Key Dependencies | Quality Gate / Approval | In Scope? | Owner | Target Date | Status
1 — ASSESS | Process | 1.PRO.01 | Process taxonomy (L1–L3) | Hierarchical catalog of all in-scope processes: L1 (end-to-end value streams, e.g., S2P, R2R, O2C), L2 (functional processes, e.g., Invoice Receipt, Payment Run), L3 (sub-processes/activities). Foundation for all downstream scoping. | Process Excellence Lead | Fachbereich SME availability | SteerCo sign-off on L1–L2 scope
1 — ASSESS | Process | 1.PRO.02 | Current-state process maps (as-is) | Visual process flows for each L2 process showing steps, roles, systems, handoffs, decision points, and exceptions. BPMN or swim-lane format. | Process Analysts | L1–L3 taxonomy approved | Process owner review & sign-off
1 — ASSESS | Process | 1.PRO.03 | Process volume & transaction analysis | Quantified view: transaction counts, cycle times, FTE effort per L2 process, seasonality patterns, error/rework rates. Basis for capacity planning. | Process Analysts + Finance | System data access (SAP, ERP) | Data validated by process owners
1 — ASSESS | Process | 1.PRO.04 | Process maturity assessment | Structured scoring of each L2 process against maturity dimensions: standardization, automation, documentation, governance, performance management. | Process Excellence Lead | As-is maps complete | Calibrated across all domains
1 — ASSESS | Process | 1.PRO.05 | Exception & workaround inventory | Catalog of manual workarounds, shadow IT tools, offline spreadsheets, and non-standard process variants by country/entity. | Process Analysts | Process mapping interviews | Validated by local teams
1 — ASSESS | Process | 1.PRO.06 | Pain point & quick-win register | Prioritized list of process inefficiencies, bottlenecks, and root causes. Quick wins (<90 days, low effort) flagged separately. | Workstream Leads | As-is analysis complete | Prioritized by impact/effort
1 — ASSESS | Process | 1.PRO.07 | Regulatory & compliance constraint map | Inventory of statutory, regulatory, and compliance requirements per country/entity that constrain process standardization (e.g., local tax rules, statutory reporting). | Legal / Compliance + Process | Country scope confirmed | Legal review
1 — ASSESS | People & Org | 1.PEO.01 | Talent map (current state) | FTE inventory by function, role, location, grade, tenure, language skills, and process domain coverage. Identifies key-person dependencies. | HR + Workstream Leads | Org chart & HR data access | HR data validation
1 — ASSESS | People & Org | 1.PEO.02 | Skills & competency matrix | Assessment of current workforce skills vs. future-state requirements: process knowledge, language proficiency, system skills, analytical capability. | HR + Process Leads | Talent map complete | Manager calibration
1 — ASSESS | People & Org | 1.PEO.03 | Role catalog (current state) | Inventory of all unique job titles and roles performing in-scope work, mapped to L2 processes. Identifies role fragmentation and overlap. | HR | Process taxonomy + talent map | HR sign-off
1 — ASSESS | People & Org | 1.PEO.04 | Stakeholder map & influence analysis | Mapping of all key stakeholders (Vorstand, Fachbereich heads, Betriebsrat, IT, HR) with influence level, attitude to change, engagement strategy. | Program Lead + Change | Org structure understood | Restricted — programme lead only
1 — ASSESS | People & Org | 1.PEO.05 | Employee sentiment baseline | Pulse survey or structured interviews to capture current engagement, change readiness, and concerns before any announcements. | HR / Change Management | Communication sequencing agreed | Betriebsrat alignment on survey design
1 — ASSESS | People & Org | 1.PEO.06 | Retention risk assessment | Identification of critical knowledge holders and flight-risk individuals. Retention actions and knowledge-transfer priorities. | HR + Line Managers | Talent map + skills matrix | Restricted — HR + programme lead
1 — ASSESS | Technology | 1.TEC.01 | System & tool inventory | Comprehensive list of all IT systems, tools, and applications used in in-scope processes: ERP (SAP modules), middleware, reporting tools, RPA bots, shadow IT. | IT + Process Analysts | Process mapping complete | IT architecture review
1 — ASSESS | Technology | 1.TEC.02 | Data quality & master data assessment | Assessment of master data completeness, accuracy, and consistency: vendor master, customer master, chart of accounts, cost center structure. | IT / Data + Process Owners | System inventory complete | Data steward sign-off
1 — ASSESS | Technology | 1.TEC.03 | Integration & interface map | Documentation of all system interfaces, data flows, and integration points between in-scope systems and upstream/downstream applications. | IT Architecture | System inventory complete | IT architecture review
1 — ASSESS | Technology | 1.TEC.04 | Automation & RPA baseline | Inventory of existing automation (RPA bots, macros, scripts, workflows) with utilization rates, maintenance status, and scalability assessment. | IT / Automation CoE | System inventory complete | Automation team review
1 — ASSESS | Technology | 1.TEC.05 | IT infrastructure readiness assessment | Assessment of network, security, access management, VPN, telephony, and hardware readiness for multi-site operations. | IT Infrastructure | Location shortlist available | IT security sign-off
1 — ASSESS | Governance | 1.GOV.01 | Decision-rights map (current state) | Documentation of who decides what today: process ownership, budget authority, escalation paths, approval thresholds. Identifies gaps and overlaps. | Program Lead | Stakeholder map complete | Vorstand validation
1 — ASSESS | Governance | 1.GOV.02 | Current governance & reporting inventory | Inventory of existing governance forums, reporting cadences, KPI dashboards, and management reviews relevant to in-scope processes. | Process Owners + Finance | Stakeholder map complete | Process owner review
1 — ASSESS | Change & Comms | 1.CHA.01 | Change readiness assessment | Structured evaluation of organizational readiness for transformation: leadership alignment, change history, cultural factors, communication channels. | Change Management Lead | Stakeholder map complete | Change lead + HR review
1 — ASSESS | Change & Comms | 1.CHA.02 | Communication channel inventory | Mapping of existing internal communication channels, cadences, and effectiveness (town halls, intranet, newsletters, team meetings, Betriebsrat forums). | Change / Comms | Stakeholder map complete | Comms team review
1 — ASSESS | Change & Comms | 1.CHA.03 | Co-determination requirements analysis | Legal analysis of §111 BetrVG applicability, SE co-determination regime, Betriebsrat information and consultation rights, timeline constraints. | Legal + HR + Program Lead | Legal entity structure confirmed | Legal counsel sign-off
1 — ASSESS | Location & Infra | 1.LOC.01 | Location long-list & scoring framework | Structured evaluation of candidate locations against weighted criteria (talent, cost, infrastructure, risk, strategic fit). See separate Location Strategy workbook. | Program Lead + HR | Scope & FTE volume confirmed | SteerCo shortlist approval
1 — ASSESS | Location & Infra | 1.LOC.02 | Existing asset & entity register | Inventory of company-owned/leased properties, legal entities, and existing operations in candidate locations. | Finance / Legal / Facilities | Location long-list defined | Finance validation
1 — ASSESS | Finance & Business Case | 1.FIN.01 | Current cost baseline (cost-to-serve) | Fully-loaded cost of performing in-scope processes today: labor (FTE × cost), technology, facilities, management overhead, third-party spend. By entity and process domain. | Finance + HR | Talent map + system inventory | CFO / Finance review
1 — ASSESS | Finance & Business Case | 1.FIN.02 | Benchmarking analysis | Comparison of current cost-to-serve, productivity, and quality metrics against external benchmarks (Hackett, APQC, SSON) and industry peers. | Program Lead / Finance | Cost baseline complete | CFO review
1 — ASSESS | Finance & Business Case | 1.FIN.03 | Feasibility study / preliminary business case | High-level financial assessment: estimated savings, investment required, payback period, risk-adjusted NPV. Go/no-go recommendation. | Program Lead + Finance | All Phase 1 deliverables | Vorstand / SteerCo approval
2 — DESIGN | Process | 2.PRO.01 | Target-state process maps (to-be) | Redesigned process flows for each L2 process: standardized, simplified, automation-ready. Incorporates S/4HANA process design where applicable. | Process Excellence + S/4HANA team | As-is maps + S/4HANA blueprint | Process owner + IT sign-off
2 — DESIGN | Process | 2.PRO.02 | Process scope matrix (in/out) | Definitive scope document: which L2/L3 processes move to the service center, which stay local, which are eliminated or automated. By entity. | Program Lead + Process Leads | Process taxonomy + feasibility | SteerCo approval — binding
2 — DESIGN | Process | 2.PRO.03 | Standardization gap analysis | Country-by-country delta between current and target process, identifying what must change, what can be harmonized, and what requires local exception. | Process Analysts | To-be maps + regulatory map | Process owner review per country
2 — DESIGN | Process | 2.PRO.04 | SLA & KPI framework (draft) | Definition of service levels, KPIs, and performance targets for each process domain. Includes measurement methodology, reporting frequency, escalation triggers. | Process Excellence + Governance | To-be process design approved | Fachbereich sign-off
2 — DESIGN | Process | 2.PRO.05 | Process documentation standards | Template and standards for SOPs, work instructions, process maps, and desktop procedures. Ensures consistency for knowledge transfer. | Process Excellence / KM | To-be maps approved | Quality review
2 — DESIGN | Process | 2.PRO.06 | Automation opportunity register | Prioritized pipeline of automation candidates (RPA, workflow, AI/ML) mapped to to-be processes, with estimated effort, benefit, and sequencing. | Automation CoE / IT | To-be maps + system inventory | IT + process owner review
2 — DESIGN | People & Org | 2.PEO.01 | Target Operating Model (TOM) | Comprehensive future-state design: organizational structure, reporting lines, spans of control, role allocation (HQ vs. service center), governance model. | Program Lead | Process scope matrix approved | Vorstand / SteerCo approval
2 — DESIGN | People & Org | 2.PEO.02 | Job architecture (future state) | Catalog of all future-state roles: job descriptions, grade levels, competency requirements, career paths. Covers service center and retained organization. | HR + Process Leads | TOM approved | HR sign-off + Betriebsrat
2 — DESIGN | People & Org | 2.PEO.03 | FTE capacity model | Detailed headcount plan: target FTEs per role, per process domain, per location. Based on volume, productivity targets, and automation assumptions. | Program Lead + Finance | Process scope + automation register | Finance + HR validation
2 — DESIGN | People & Org | 2.PEO.04 | Sending-side people plan | Plan for impacted employees at sending locations: redeployment, reskilling, voluntary separation, social plan. Betriebsrat-aligned. | HR + Legal + Program Lead | TOM + FTE model approved | Betriebsrat agreement required
2 — DESIGN | People & Org | 2.PEO.05 | Receiving-side talent acquisition strategy | Recruitment plan for service center: employer branding, sourcing channels, selection criteria, onboarding design, ramp-up timeline. | HR / Recruitment | Location + FTE model confirmed | HR lead sign-off
2 — DESIGN | People & Org | 2.PEO.06 | Training needs analysis & curriculum design | Gap analysis between current skills and future-state requirements. Training curriculum for technical skills, process knowledge, soft skills, language. | HR / L&D + Process Leads | Job architecture + skills matrix | L&D + process owner review
2 — DESIGN | People & Org | 2.PEO.07 | Retention & incentive program design | Design of retention bonuses, knowledge-transfer incentives, and transition support for critical sending-side employees. | HR + Finance | Retention risk assessment | HR + Finance + Legal approval
2 — DESIGN | Technology | 2.TEC.01 | IT target architecture | Future-state IT landscape for service center operations: ERP access, workflow tools, ticketing systems, collaboration platforms, telephony, reporting. | IT Architecture | TOM + process scope approved | IT SteerCo / CIO approval
2 — DESIGN | Technology | 2.TEC.02 | Master data cleanse plan | Detailed plan for cleaning, harmonizing, and governing master data prior to transition: vendor master, customer master, CoA, cost centers. | IT / Data + Process Owners | Data quality assessment complete | Data steward + IT sign-off
2 — DESIGN | Technology | 2.TEC.03 | System access & authorization concept | Role-based access control design for all in-scope systems at the service center. Segregation of duties, approval workflows, audit trail. | IT Security + Process | Job architecture + IT architecture | IT Security + Audit sign-off
2 — DESIGN | Technology | 2.TEC.04 | Tool selection & procurement plan | Evaluation and selection of new tools required (ticketing, workflow, KM, telephony, BI). Procurement timeline and budget. | IT + Program Lead | IT target architecture approved | IT + Finance approval
2 — DESIGN | Technology | 2.TEC.05 | Data migration & cutover strategy | Plan for migrating data, configurations, and customizations required for service center operations. Cutover sequence and rollback plan. | IT + Process | IT architecture + process scope | IT + process owner sign-off
2 — DESIGN | Governance | 2.GOV.01 | GBS governance blueprint | Complete governance model: steering committee charter, decision-rights matrix (RACI), escalation framework, reporting cadence, performance review cycle. | Program Lead + Governance | TOM approved | Vorstand / SteerCo approval
2 — DESIGN | Governance | 2.GOV.02 | Service catalog | Formal catalog of all services delivered by the GBS center, with service descriptions, SLAs, pricing model (if applicable), and ordering process. | Process Excellence + Governance | Process scope + SLA framework | Fachbereich sign-off
2 — DESIGN | Governance | 2.GOV.03 | Risk register & mitigation plan | Comprehensive risk register with likelihood, impact, owner, mitigation actions, and review cadence. Updated at every SteerCo. | Program Lead / PMO | All Phase 2 deliverables | SteerCo review
2 — DESIGN | Governance | 2.GOV.04 | Compliance & audit framework | Design of internal controls, SOX considerations, audit readiness requirements, and compliance monitoring for the service center. | Internal Audit / Compliance | Process scope + governance model | Audit + Legal sign-off
2 — DESIGN | Change & Comms | 2.CHA.01 | Change management strategy & plan | End-to-end change plan: stakeholder engagement roadmap, communication calendar, training plan, resistance management approach, feedback mechanisms. | Change Management Lead | Stakeholder map + TOM approved | Program Lead + HR approval
2 — DESIGN | Change & Comms | 2.CHA.02 | Communication plan (multi-audience) | Tailored communication plans for each audience: Vorstand, Betriebsrat, Fachbereich heads, impacted employees, receiving-site employees, customers/suppliers. | Change / Comms | Change strategy approved | Legal review for BR comms
2 — DESIGN | Change & Comms | 2.CHA.03 | Betriebsrat negotiation package | §111 BetrVG documentation: Interessenausgleich proposal, Sozialplan framework, information packages, timeline for consultation process. | Legal + HR + Program Lead | TOM + people plan approved | Legal counsel mandatory
2 — DESIGN | Change & Comms | 2.CHA.04 | Narrative & FAQ library | Approved messaging for all stakeholder groups: key messages, talking points, FAQ documents, manager briefing kits. | Change / Comms + Legal | Communication plan approved | Legal + Vorstand approval
2 — DESIGN | Location & Infra | 2.LOC.01 | Location decision & approval | Final location recommendation with scoring, sensitivity analysis, site visit findings, and SteerCo/Vorstand approval. | Program Lead | Location scoring complete | Vorstand approval — binding
2 — DESIGN | Location & Infra | 2.LOC.02 | Office design & fit-out plan | Detailed space plan: floor layout, workstations, meeting rooms, IT infrastructure, security, accessibility. Aligned with FTE ramp-up plan. | Facilities / Real Estate + IT | Location decision + FTE model | Facilities + IT + Finance approval
2 — DESIGN | Location & Infra | 2.LOC.03 | Legal entity setup plan | Plan for establishing or repurposing legal entity at service center location: company registration, tax registration, bank accounts, employment contracts. | Legal + Tax + Finance | Location decision approved | Legal + Tax sign-off
2 — DESIGN | Location & Infra | 2.LOC.04 | BCP / DRP design | Business continuity and disaster recovery plan for the service center: failover procedures, backup sites, communication protocols, recovery time objectives. | IT + Operations + Risk | IT architecture + location confirmed | Risk + IT + SteerCo approval
2 — DESIGN | Finance & Business Case | 2.FIN.01 | Detailed business case | Full financial model: one-time investment, recurring costs, labor savings, productivity gains, risk contingency. NPV, IRR, payback period. Sensitivity scenarios. | Finance + Program Lead | All Phase 2 deliverables | CFO + Vorstand approval — binding
2 — DESIGN | Finance & Business Case | 2.FIN.02 | Benefits realization framework | Methodology for tracking and reporting realized vs. planned benefits: savings categories, measurement points, reporting cadence, accountability. | Finance + Program Lead | Business case approved | CFO + SteerCo sign-off
2 — DESIGN | Finance & Business Case | 2.FIN.03 | Investment approval & funding plan | Capital and operating expenditure approval, phased funding schedule, budget allocation by workstream. | Finance | Business case approved | CFO + Vorstand approval
3 — BUILD | Process | 3.PRO.01 | Standard Operating Procedures (SOPs) | Detailed, step-by-step work instructions for every L3 process to be performed at the service center. Screenshots, system paths, exception handling. | Process Excellence + SMEs | To-be maps + system access confirmed | Process owner sign-off
3 — BUILD | Process | 3.PRO.02 | Desktop procedure library | Quick-reference guides for daily operational tasks: system navigation, transaction codes, approval workflows, reporting procedures. | Process Analysts + KM | SOPs complete | User acceptance testing
3 — BUILD | Process | 3.PRO.03 | Knowledge management repository setup | Structured, searchable repository (SharePoint, Confluence, etc.) for all process documentation, SOPs, FAQs, training materials, contact lists. | KM Lead + IT | Documentation standards + IT tools | KM lead + IT sign-off
3 — BUILD | Process | 3.PRO.04 | SLA & KPI baseline measurement | Baseline measurement of all defined KPIs at sending locations before transition. Establishes the benchmark for post-transition performance comparison. | Process Excellence + Operations | SLA framework approved | Process owner validation
3 — BUILD | People & Org | 3.PEO.01 | Recruitment execution (receiving side) | Active recruitment against the talent acquisition strategy: job postings, sourcing, interviews, offers, onboarding scheduling. Phased per ramp-up plan. | HR / Recruitment | Job architecture + budget approved | HR lead sign-off per cohort
3 — BUILD | People & Org | 3.PEO.02 | Onboarding program | Structured onboarding: company orientation, process training schedule, buddy assignment, system access provisioning, 30/60/90-day milestones. | HR + L&D + Operations | Training curriculum designed | HR + Operations review
3 — BUILD | People & Org | 3.PEO.03 | Training materials & delivery | Complete training package: e-learning modules, classroom materials, hands-on exercises, assessment tests. Per process domain and role. | L&D + Process SMEs | SOPs + training needs analysis | L&D + process owner sign-off
3 — BUILD | People & Org | 3.PEO.04 | Sending-side transition support | Execution of the people plan: individual consultations, redeployment matching, outplacement support, social plan implementation. | HR + Works Council | Betriebsrat agreements in place | HR + Legal — ongoing
3 — BUILD | People & Org | 3.PEO.05 | Organization chart & reporting lines (live) | Finalized org chart with named individuals, reporting lines, spans of control, and effective dates. Both service center and retained organization. | HR + Program Lead | Recruitment + TOM confirmed | HR + Vorstand sign-off
3 — BUILD | People & Org | 3.PEO.06 | Performance management framework | KPIs, review cadence, goal-setting process, and feedback mechanisms for service center employees. Aligned with company-wide HR policies. | HR + Operations | Job architecture + SLA framework | HR sign-off
3 — BUILD | Technology | 3.TEC.01 | IT infrastructure deployment | Physical and virtual infrastructure: network, servers/cloud, workstations, printers, telephony, video conferencing, security systems. | IT Infrastructure | Office fit-out + IT architecture | IT sign-off + security audit
3 — BUILD | Technology | 3.TEC.02 | System access provisioning | Creation of user accounts, role assignments, authorization profiles for all service center employees across all in-scope systems. | IT + IT Security | Authorization concept + recruitment | IT Security audit
3 — BUILD | Technology | 3.TEC.03 | Master data cleanse execution | Execution of the cleanse plan: vendor master deduplication, CoA harmonization, cost center alignment, customer master cleanup. | Data Team + Process Owners | Cleanse plan approved | Data steward sign-off per domain
3 — BUILD | Technology | 3.TEC.04 | Tool implementation & configuration | Setup, configuration, and testing of new tools (ticketing, workflow, KM, BI dashboards) per the tool selection plan. | IT + Vendors | Tool selection + procurement done | UAT by end users
3 — BUILD | Technology | 3.TEC.05 | Integration & interface testing | End-to-end testing of all system interfaces, data flows, and integrations between service center and HQ/entity systems. | IT + Process | All systems deployed + configured | IT + process owner sign-off
3 — BUILD | Technology | 3.TEC.06 | IT support model & helpdesk setup | Establishment of IT support for service center: helpdesk, escalation paths, SLAs, remote support capability, on-site support schedule. | IT Operations | IT infrastructure deployed | IT Operations sign-off
3 — BUILD | Governance | 3.GOV.01 | Governance activation | Launch of governance forums: SteerCo meetings, operational reviews, workstream cadences. Calendar, attendees, templates, and reporting dashboards live. | PMO / Program Lead | Governance blueprint approved | First SteerCo meeting held
3 — BUILD | Governance | 3.GOV.02 | Operational reporting dashboard | Live reporting dashboard: KPIs, SLA performance, volume tracking, staffing levels, open issues. Accessible to service center management and stakeholders. | BI / IT + Operations | KPI framework + IT tools | Operations + SteerCo review
3 — BUILD | Governance | 3.GOV.03 | Issue & escalation log | Structured log for tracking operational issues, escalations, and resolutions. Integrated into governance cadence. | PMO / Operations | Governance forums active | Ongoing — reviewed at every ops review
3 — BUILD | Change & Comms | 3.CHA.01 | Stakeholder communication execution | Delivery of communication plan: town halls, team briefings, FAQ sessions, intranet updates, manager cascades. Per the approved calendar. | Change / Comms | Communication plan + narrative library | Change lead tracks delivery + feedback
3 — BUILD | Change & Comms | 3.CHA.02 | Change agent network activation | Identification, training, and activation of change agents in sending and receiving locations. Regular check-ins and feedback loops. | Change Management Lead | Change strategy approved | Change lead review
3 — BUILD | Change & Comms | 3.CHA.03 | Manager readiness program | Targeted preparation for managers in sending and receiving organizations: managing uncertainty, leading through change, difficult conversations. | Change / L&D / HR | Manager list + change plan | HR + Change lead sign-off
3 — BUILD | Location & Infra | 3.LOC.01 | Office fit-out & commissioning | Physical completion of service center: furniture, IT cabling, security, access control, signage, common areas. Handover to operations. | Facilities / Real Estate | Office design plan + budget | Facilities + Health & Safety sign-off
3 — BUILD | Location & Infra | 3.LOC.02 | Legal entity activation | Completion of legal entity setup: registration, tax ID, bank accounts, employment contract templates, payroll setup, statutory registrations. | Legal + Tax + Finance + HR | Legal entity plan approved | Legal + Tax + Finance sign-off
3 — BUILD | Location & Infra | 3.LOC.03 | Vendor & supplier setup (local) | Establishment of local vendor relationships: office supplies, catering, facility management, cleaning, security services. | Procurement / Facilities | Office location confirmed | Procurement sign-off
3 — BUILD | Finance & Business Case | 3.FIN.01 | Budget activation & cost tracking | Activation of project and operational budgets with tracking mechanisms. Monthly actual vs. plan reporting to SteerCo. | Finance / PMO | Investment approval confirmed | CFO + PMO review monthly
3 — BUILD | Finance & Business Case | 3.FIN.02 | Transfer pricing & intercompany setup | Design and implementation of transfer pricing arrangements between service center entity and served entities. Tax-compliant documentation. | Tax + Finance + Legal | Legal entity active + business case | Tax + Legal sign-off
4 — TRANSITION | Process | 4.PRO.01 | Knowledge transfer plan (per wave) | Detailed plan per transition wave: which processes, which entities, which timeline, KT methodology (classroom, shadowing, reverse-shadowing, parallel run). | Transition Manager + Process | SOPs + receiving team onboarded | Transition manager sign-off per wave
4 — TRANSITION | Process | 4.PRO.02 | Knowledge transfer execution log | Tracking of KT sessions: topics covered, attendees, assessment scores, open questions, readiness rating per process and individual. | KT Leads + Process SMEs | KT plan approved + team assigned | KT lead + process owner review
4 — TRANSITION | Process | 4.PRO.03 | Parallel run execution & sign-off | Parallel processing of live transactions at both sending and receiving sites. Error tracking, comparison, issue resolution. Formal sign-off to proceed. | Transition Manager + Operations | KT complete + systems live | Process owner + operations sign-off
4 — TRANSITION | Process | 4.PRO.04 | Go-live checklist (per wave) | Comprehensive checklist covering all prerequisites for cutover: system readiness, team readiness, documentation complete, governance active, comms sent. | Transition Manager / PMO | All Build deliverables complete | SteerCo go/no-go decision
4 — TRANSITION | Process | 4.PRO.05 | Hypercare plan & execution | Intensive post-go-live support period (typically 4–8 weeks): dedicated SME support, daily issue reviews, escalation fast-track, performance monitoring. | Operations + Process SMEs | Go-live decision approved | Operations + SteerCo review
4 — TRANSITION | Process | 4.PRO.06 | Process handover certificate | Formal sign-off document confirming successful transfer of process responsibility from sending to receiving organization. Per process domain and entity. | Process Owner + Operations | Hypercare complete + KPIs stable | Process owner + Vorstand sign-off
4 — TRANSITION | People & Org | 4.PEO.01 | Team readiness assessment (per wave) | Structured assessment of receiving team readiness: knowledge test scores, process simulation results, system proficiency, confidence rating. | L&D + Operations | KT + training complete | Operations + HR sign-off
4 — TRANSITION | People & Org | 4.PEO.02 | Sending-side offboarding (per wave) | Managed transition of sending-side employees per the agreed people plan: exit interviews, knowledge documentation, equipment return, access revocation. | HR + Line Managers | Process handover per wave | HR sign-off
4 — TRANSITION | People & Org | 4.PEO.03 | Buddy / SME support assignments | Assignment of experienced SMEs from sending side to support receiving team during transition and hypercare. Schedule, availability, escalation paths. | Transition Manager + HR | KT plan + retention agreements | Transition manager review
4 — TRANSITION | Technology | 4.TEC.01 | System cutover execution | Execution of technical cutover: access migration, interface redirection, batch job rescheduling, print routing, email forwarding, telephony switchover. | IT + Process | IT readiness confirmed | IT + operations sign-off
4 — TRANSITION | Technology | 4.TEC.02 | Post-cutover IT stabilization | Dedicated IT support during first weeks post-go-live: priority incident handling, access troubleshooting, performance monitoring, defect resolution. | IT Operations / Helpdesk | System cutover complete | IT Operations review
4 — TRANSITION | Governance | 4.GOV.01 | Transition governance cadence | Intensified governance during transition: daily stand-ups, weekly SteerCo, issue escalation fast-track, risk dashboard, decision log. | PMO / Program Lead | Go-live decision approved | SteerCo review
4 — TRANSITION | Governance | 4.GOV.02 | Lessons learned (per wave) | Structured capture of what worked, what didn't, and what to change for next wave. Fed into continuous improvement and next-wave planning. | Transition Manager + PMO | Hypercare complete per wave | PMO review + SteerCo debrief
4 — TRANSITION | Change & Comms | 4.CHA.01 | Go-live communications (per wave) | Targeted communications to all stakeholders at go-live: what's changing, who to contact, FAQ, escalation paths. Sent-side and received-side versions. | Change / Comms | Go-live decision + narrative library | Change lead + Legal review
4 — TRANSITION | Change & Comms | 4.CHA.02 | Feedback collection & response | Structured feedback mechanisms post-go-live: pulse surveys, feedback forms, town halls, manager check-ins. Responses tracked and actioned. | Change / HR | Go-live complete | Change lead review
5 — OPTIMIZE | Process | 5.PRO.01 | Continuous improvement (CI) program | Structured CI framework: idea pipeline, Kaizen events, Lean methodology, root cause analysis, improvement tracking. Embedded in operations. | Operations / CI Lead | Steady-state operations | Operations review quarterly
5 — OPTIMIZE | Process | 5.PRO.02 | Process performance review (quarterly) | Quarterly deep-dive on process KPIs: SLA compliance, productivity, quality, cost-to-serve. Trend analysis, root causes, improvement actions. | Process Excellence + Operations | KPI dashboard live | SteerCo quarterly review
5 — OPTIMIZE | Process | 5.PRO.03 | Automation pipeline execution | Ongoing implementation of automation opportunities: RPA, workflow optimization, AI/ML use cases. Prioritized by ROI and feasibility. | Automation CoE / IT | Automation register + IT capacity | IT + Operations review
5 — OPTIMIZE | Process | 5.PRO.04 | Scope expansion roadmap | Plan for adding new processes, entities, or functions to the service center scope. Phased approach with business case per expansion. | Program Lead + Process Leads | Stabilization confirmed | SteerCo approval per expansion
5 — OPTIMIZE | People & Org | 5.PEO.01 | Employee engagement survey (annual) | Annual engagement measurement for service center: satisfaction, development opportunities, manager effectiveness, retention intent. | HR | Steady-state operations | HR + Operations review
5 — OPTIMIZE | People & Org | 5.PEO.02 | Career development & succession planning | Career path framework for service center employees: promotion criteria, rotation programs, leadership development, succession for key roles. | HR + Operations | Performance management live | HR review annually
5 — OPTIMIZE | People & Org | 5.PEO.03 | Talent review & workforce planning | Annual review of headcount, skills mix, attrition, and pipeline. Aligned with scope expansion and automation impact on FTE needs. | HR + Operations + Finance | 12+ months of operational data | HR + Finance + Operations
5 — OPTIMIZE | Governance | 5.GOV.01 | GBS maturity assessment | Periodic assessment of GBS maturity against industry benchmarks (Hackett, SSON). Identifies gaps and sets improvement targets. | Program Lead / GBS Head | 12+ months steady-state | SteerCo review — annually
5 — OPTIMIZE | Governance | 5.GOV.02 | Benefits realization report | Periodic report comparing actual realized benefits vs. business case: cost savings, productivity, quality, strategic value. Variance analysis. | Finance + GBS Head | Benefits framework + 6+ months data | CFO + SteerCo review
5 — OPTIMIZE | Governance | 5.GOV.03 | Value creation & strategic contribution review | Annual assessment of GBS contribution beyond cost: analytics, decision support, innovation, process intelligence, strategic projects. | GBS Head + Vorstand Sponsor | 18+ months of operations | Vorstand review — annually

## Enablers & Prerequisites
CROSS-CUTTING ENABLERS & PREREQUISITES — Must be resolved before / during transition
# | Category | Enabler | Description & Why It Matters | Typical Owner | Blocks Which Phase | Target Date | Status
E01 | Data & Master Data | Master data cleanse — Vendor master | Duplicate, inactive, and incomplete vendor records must be cleansed before transition. Dirty vendor master = payment errors, duplicate invoices, audit findings. | Data Team + AP Process Owner | 3 — BUILD
E02 | Data & Master Data | Master data cleanse — Customer master | Customer master accuracy drives O2C process quality: credit management, invoicing, dunning. Cleanse before O2C transition. | Data Team + AR Process Owner | 3 — BUILD
E03 | Data & Master Data | Master data cleanse — Chart of Accounts | CoA harmonization across entities is a prerequisite for R2R standardization. Must align with S/4HANA design. | Finance + IT (S/4HANA) | 2 — DESIGN
E04 | Data & Master Data | Master data cleanse — Cost center structure | Cost center harmonization required for consistent reporting and allocation logic across entities. | Controlling + IT | 2 — DESIGN
E05 | Data & Master Data | Master data governance model | Ongoing governance: who creates, changes, approves master data. Roles, workflows, quality checks. Without this, cleanse benefits erode. | Data Governance Lead | 3 — BUILD
E06 | Systems & Tools | System/tool inventory (complete) | Every system, tool, macro, and shadow-IT workaround used in in-scope processes must be inventoried. You cannot transition what you don't know. | IT + Process Analysts | 1 — ASSESS
E07 | Systems & Tools | S/4HANA alignment & sequencing | GBS process design must align with S/4HANA blueprint. Sequencing conflicts (which goes first?) must be resolved at SteerCo level. | Program Lead + S/4HANA Lead | 2 — DESIGN
E08 | Systems & Tools | ERP access for service center | SAP/ERP access from the service center location: VPN, Fiori, authorization profiles. Must be tested before KT starts. | IT Security + IT Infra | 3 — BUILD
E09 | Systems & Tools | Workflow & ticketing tool | Standardized tool for service requests, issue tracking, and SLA monitoring. Must be live before first transition wave. | IT + Operations | 3 — BUILD
E10 | Systems & Tools | Knowledge management platform | Central, searchable repository for SOPs, FAQs, process documentation. Must be populated and tested before KT. | KM Lead + IT | 3 — BUILD
E11 | Systems & Tools | BI / reporting tool for KPIs | Operational dashboard for real-time KPI monitoring. Must be configured and tested before go-live. | BI / IT + Operations | 3 — BUILD
E12 | People & Organization | Job descriptions — current state | Documented job descriptions for all in-scope roles at sending locations. Baseline for role redesign and Betriebsrat discussions. | HR | 1 — ASSESS
E13 | People & Organization | Job descriptions — future state | New job descriptions for all service center roles and retained-organization roles. Required for recruitment and Betriebsrat. | HR + Process Leads | 2 — DESIGN
E14 | People & Organization | Language proficiency requirements | Defined language requirements per role and process domain. Non-negotiable for recruitment and cannot be fixed post-hire. | HR + Process Leads | 2 — DESIGN
E15 | People & Organization | Betriebsrat engagement (pre-condition) | Betriebsrat must be informed and consulted per §111 BetrVG BEFORE any employee communications about structural changes. | Legal + HR + Program Lead | 2 — DESIGN
E16 | People & Organization | Social plan framework | Agreed framework for handling impacted employees: severance, redeployment, retraining. Must be in place before transition announcements. | HR + Legal + Betriebsrat | 2 — DESIGN
E17 | People & Organization | Retention agreements for critical SMEs | Retention bonuses or agreements for key sending-side employees needed during KT period. If they leave early, KT fails. | HR + Finance | 3 — BUILD
E18 | Governance & Legal | Legal entity structure confirmed | Service center legal entity: existing or new? Jurisdictional, tax, employment law implications must be resolved early. | Legal + Tax + Finance | 2 — DESIGN
E19 | Governance & Legal | Transfer pricing arrangement | Intercompany pricing model for services rendered by the service center. Tax-compliant, documented, defensible. | Tax + Finance + Legal | 3 — BUILD
E20 | Governance & Legal | Data protection impact assessment (DPIA) | GDPR assessment for processing personal data at the service center location. Required before any data transfer. | DPO / Legal | 2 — DESIGN
E21 | Governance & Legal | Insurance & liability review | Review of professional indemnity, employer liability, and operational insurance for service center location. | Legal + Risk + Finance | 3 — BUILD
E22 | Governance & Legal | Intellectual property & confidentiality | NDA frameworks, IP protection, and confidentiality agreements for service center employees and any third parties. | Legal + HR | 3 — BUILD
E23 | Infrastructure & Facilities | Office space secured | Signed lease or confirmed allocation of company-owned space. Must be secured before fit-out planning can proceed. | Real Estate / Facilities | 2 — DESIGN
E24 | Infrastructure & Facilities | IT network & connectivity | WAN/VPN connectivity between service center and HQ/data center. Bandwidth, latency, and redundancy requirements met. | IT Infrastructure | 3 — BUILD
E25 | Infrastructure & Facilities | Physical security & access control | Badge access, CCTV, visitor management, clean-desk policy, server room security. Must meet corporate security standards. | Facilities + IT Security | 3 — BUILD
E26 | Infrastructure & Facilities | Workstation & equipment procurement | Laptops, monitors, docking stations, headsets, printers. Lead times can be 8–12 weeks — order early. | IT + Procurement | 3 — BUILD