## Dashboard
GBS TRANSFORMATION PROGRAMME TRACKER
Process Harmonisation & AI-First Transformation
| 8 |  | 3 | 1 |  | 0 | 10
| TOTAL WORKSTREAMS |  | ON TRACK | AT RISK |  | BLOCKED / OFF TRACK | OPEN ACTIONS
| PROGRAMME DETAILS |  |  |  | KEY DECISIONS & ESCALATIONS
| Programme Lead | [Name] |  |  | # | Decision / Escalation | Owner | Due | Status
| Start Date | 01-Jun-2026 |  |  | 1
| Target Go-Live | [TBD] |  |  | 2
| Location |  |  |  | 3
| Last Updated | 08-Jun-2026 |  |  | 4
5

## Workstreams
TRANSFORMATION WORKSTREAMS
Workstream | Tower / Function | Stream Lead | Start Date | Target End | Status | % Complete | Phase | Key Dependency | Next Milestone | Comments
P2P Process Harmonisation | Accounts Payable | [Lead] | 01-Jul-2026 | 31-Dec-2026 | On Track | 0% | Discovery | ERP landscape mapping | AS-IS documentation complete
O2C Standardisation | Accounts Receivable | [Lead] | 01-Jul-2026 | 28-Feb-2027 | On Track | 0% | Planning | Credit policy alignment | Scope sign-off
R2R Process Redesign | General Ledger | [Lead] | 01-Aug-2026 | 31-Mar-2027 | Not Started | 0% | Pre-Discovery | Chart of accounts review | Kick-off meeting
Master Data Governance | Cross-Functional | [Lead] | 15-Jul-2026 | 30-Jun-2027 | At Risk | 0% | Discovery | MDM tool selection | Data quality baseline | Multiple legacy systems
AI-First Automation Pilot | Innovation | [Lead] | 01-Sep-2026 | 31-Dec-2026 | Not Started | 0% | Pre-Discovery | Use case prioritisation | Pilot scope approved
GBS Operating Model | Programme Office | [Lead] | 01-Jun-2026 | 30-Sep-2026 | On Track | 15% | Discovery | Stakeholder alignment | Target operating model v1
Shared Services Migration Wave 1 | HR / Finance | [Lead] | 01-Oct-2026 | 30-Jun-2027 | Not Started | 0% | Pre-Discovery | Service catalogue | Migration readiness assessment
Continuous Improvement Framework | Operational Excellence | [Lead] | 01-Aug-2026 | Ongoing | Not Started | 0% | Planning | KPI framework | Lean baseline assessment

## Actions
ACTION TRACKER
ID | Action Item | Workstream | Owner | Priority | Due Date | Status | % Done | Blocker / Dependency | Last Update | Comments
ACT-001 | Map current P2P process variants across entities | P2P Process Harmonisation | [Owner] | High | 15-Jul-2026 | Open | 0%
ACT-002 | Conduct stakeholder interviews — AP tower leads | P2P Process Harmonisation | [Owner] | High | 20-Jul-2026 | Open | 0%
ACT-003 | Define target operating model principles | GBS Operating Model | [Owner] | Critical | 30-Jun-2026 | In Progress | 30%
ACT-004 | Inventory all ERP systems and versions | Master Data Governance | [Owner] | High | 31-Jul-2026 | Open | 0% | IT landscape team availability
ACT-005 | Draft data quality assessment framework | Master Data Governance | [Owner] | Medium | 15-Aug-2026 | Open | 0% | ACT-004 completion
ACT-006 | Identify AI automation use cases — top 10 | AI-First Automation Pilot | [Owner] | High | 15-Sep-2026 | Open | 0%
ACT-007 | Benchmark GBS KPIs against SSON/Hackett data | Continuous Improvement Framework | [Owner] | Medium | 31-Aug-2026 | Open | 0%
ACT-008 | Define service catalogue for Wave 1 scope | Shared Services Migration Wave 1 | [Owner] | High | 30-Sep-2026 | Open | 0% | GBS Operating Model sign-off
ACT-009 | Align credit policy across O2C entities | O2C Standardisation | [Owner] | Medium | 31-Jul-2026 | Open | 0%
ACT-010 | Set up programme governance cadence | GBS Operating Model | [Owner] | Critical | 15-Jun-2026 | In Progress | 50% |  |  | Weekly SteerCo + bi-weekly ops review

## Risks & Issues
RISK & ISSUE REGISTER
ID | Type | Description | Workstream | Impact (1-5) | Probability (1-5) | Risk Score | Owner | Mitigation / Response | Status | Date Raised | Target Close
RSK-001 | Risk | Resistance to process standardisation from local entities | P2P Process Harmonisation | 4 | 4 | 16 | [Owner] | Change management programme; early stakeholder engagement | Open | 01-Jun-2026
RSK-002 | Risk | ERP landscape fragmentation delays harmonisation | Master Data Governance | 5 | 3 | 15 | [Owner] | Phased approach; middleware integration layer | Open | 01-Jun-2026
RSK-003 | Risk | Key resource attrition during transition | Programme Office | 4 | 3 | 12 | [Owner] | Retention packages; knowledge transfer protocol | Open | 01-Jun-2026
ISS-001 | Issue | No single source of truth for master data | Master Data Governance | 5 | 5 | 25 | [Owner] | Priority data cleansing sprint; interim golden record process | Open | 01-Jun-2026 | 31-Aug-2026
RSK-004 | Risk | AI pilot scope creep or unrealistic expectations | AI-First Automation Pilot | 3 | 4 | 12 | [Owner] | Strict MVP scope; executive sponsor alignment on success criteria | Open | 01-Jun-2026
RSK-005 | Risk | Regulatory / compliance gaps in cross-border process changes | O2C Standardisation | 4 | 2 | 8 | [Owner] | Legal review gate in design phase; compliance checklist per entity | Open | 01-Jun-2026

## Milestones
KEY MILESTONES
ID | Milestone | Workstream | Owner | Planned Date | Revised Date | Actual Date | Status | Gate / Approval | Dependencies | Notes
MS-001 | Programme kick-off & governance established | GBS Operating Model | [Owner] | 15-Jun-2026 |  |  | On Track | SteerCo approval
MS-002 | Target Operating Model v1 signed off | GBS Operating Model | [Owner] | 30-Sep-2026 |  |  | Planned | Executive Board | Stakeholder interviews complete
MS-003 | P2P AS-IS process maps complete (all entities) | P2P Process Harmonisation | [Owner] | 31-Aug-2026 |  |  | Planned | Workstream lead sign-off | Entity access confirmed
MS-004 | P2P TO-BE harmonised design approved | P2P Process Harmonisation | [Owner] | 30-Nov-2026 |  |  | Planned | Process Council | MS-003
MS-005 | Master data quality baseline established | Master Data Governance | [Owner] | 30-Sep-2026 |  |  | Planned | Data Governance Board | ERP inventory complete
MS-006 | AI pilot — 3 use cases live in production | AI-First Automation Pilot | [Owner] | 31-Dec-2026 |  |  | Planned | Innovation Board | Use case selection approved
MS-007 | Wave 1 services migrated to GBS | Shared Services Migration Wave 1 | [Owner] | 30-Jun-2027 |  |  | Planned | Transition Board | Service catalogue approved
MS-008 | Year 1 benefits realisation report | Programme Office | [Owner] | 30-Jun-2027 |  |  | Planned | CFO review | All workstreams reporting

## RACI
RACI MATRIX
R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed
Activity / Deliverable | Programme Director | Workstream Lead | Process SME | IT / SAP Team | Change Management | Finance Controller | Legal / Compliance | SteerCo | External Consultant
Programme governance & reporting | A | C | I | I | I | C | I | I | C
Target operating model design | A | R | C | C | C | C | C | I | R
AS-IS process documentation | I | A | R | C | I | C | I | I | C
TO-BE process design | A | R | R | C | C | C | C | I | C
ERP configuration / build | I | C | C | R | I | I | I | I | C
Change impact assessment | C | C | C | I | R | I | I | I | C
Data migration & cleansing | I | A | C | R | I | C | I | I | C
UAT sign-off | A | R | R | C | I | R | C | I | I
Go-live readiness assessment | A | R | C | R | R | C | C | I | C
Benefits tracking & reporting | A | R | C | I | I | R | I | I | C

## Change Log
CHANGE LOG
Date | Changed By | Sheet | Change Description | Reason
08-Jun-2026 | Julian | All | Initial tracker creation | Programme setup