## How to use
Go-Live Readiness Check — how to use
"Are we ready?" deserves an honest answer backed by evidence, not optimism.
HOW TO USE:
• Set each criterion to Ready, At risk, Not ready, or N/A — based on evidence, not hope.
• Add the evidence (a link, a sign-off, a date). "Ready" with no evidence is just a feeling.
• The rollup shows % Ready and a recommendation. Any Not ready item on a critical criterion is a NO-GO.
• Saying "we are not ready, here is the gap, here is the plan" looks far stronger six months later than waving a broken go-live through.

## Readiness
Go-Live Readiness Check
Honest readiness assessment for your area before go-live. Set each Status; the rollup gives a go / no-go signal.
# | Category | Readiness criterion | Status | Evidence / note | Owner
1 | Process | SOPs current and validated | Not ready | [link or note] | [owner]
2 | Process | Exceptions and workarounds documented | Not ready | [link or note] | [owner]
3 | People | Receivers validated solo (KT phase 4 complete) | Not ready | [link or note] | [owner]
4 | People | Hypercare roster agreed | Not ready | [link or note] | [owner]
5 | System | Access provisioned and tested | Not ready | [link or note] | [owner]
6 | System | Workflow / ticketing live | Not ready | [link or note] | [owner]
7 | Data | Master data cleansed for go-live scope | Not ready | [link or note] | [owner]
8 | Controls | Four-eyes / approvals configured | Not ready | [link or note] | [owner]
9 | Controls | Audit trail in place | Not ready | [link or note] | [owner]
10 | Cutover | Cutover plan and rollback agreed | Not ready | [link or note] | [owner]
| % Ready: | 0%
| Recommendation: | NO-GO — close Not ready items