## Overview
Knowledge Transfer Checklist (4-Phase)
GBS Insider Club — editable template
Purpose
Move every process you own through the four KT phases — Document, Demonstrate, Practise, Validate — so nothing critical lives only in someone’s head.
How to use
• List every process / knowledge item to be transferred, one per row.
• Track each through the four phases. Validate = the receiver runs it solo and the giver signs off.
• Set a target date and a named giver and receiver for each item.
• Anything still at Document or Demonstrate close to go-live is a risk — raise it on your RAID log.
Legend
Yellow cells are yours to fill in. Replace the example rows with your own. Drop-downs are provided where noted.

## KT Checklist
Knowledge Transfer Checklist — Document › Demonstrate › Practise › Validate
# | Process / knowledge item | Criticality | 1. Document | 2. Demonstrate | 3. Practise | 4. Validate | Giver | Receiver | Target date | Validated by / sign-off | Notes
1 | P2P — invoice exception handling | High | Done | Done | In Progress | Not Started | A. Giver | You | 15-Aug |  | example — replace
2 | Month-end accrual posting | Med | Done | In Progress | Not Started | Not Started | A. Giver | You | 22-Aug