## Overview
RAID Log
GBS Insider Club — editable template
Purpose
Capture Risks, Assumptions, Issues and Dependencies in one place — with an owner and a response for each — so you raise problems early without looking negative.
How to use
• Log one item per row. Pick the type: Risk, Assumption, Issue or Dependency.
• Score risks: Impact × Likelihood (1–5 each). The Score column calculates automatically.
• Every item needs an owner and a mitigation or action. An item with no owner is not managed.
• Review the log in every project check-in. Close items honestly; do not just let them age.
Legend
Yellow cells are yours to fill in. Replace the example rows with your own. Drop-downs are provided where noted.

## RAID
RAID Log — Risks · Assumptions · Issues · Dependencies
ID | Type | Description | Impact (1-5) | Likelihood (1-5) | Score | Owner | Mitigation / response / action | Status | Date raised | Target date
RSK-01 | Risk | Key SME on leave during cutover week | 4 | 4 | 16 | You | Cross-train backup; bring cutover forward 1 week | Open | 01-Jun
DEP-01 | Dependency | ERP access for receiver not yet granted | 5 | 3 | 15 | IT | Raise access request now; track to closure | Open | 01-Jun | 15-Jul